## Sheet1
Date: | 2020-02-20
No. | Document | Section/Page | TSI Question | RMA Response
1 | RFP | 2.11/p.11 | Will single channelized express lanes be considered as valid ORT experience? | Yes, if the channelized lane operates at highway speed in the toll zone. The channelized lane must have the required functionality including vehicle detection, vehicle classification, reading transponders and image capture and any other lane transaction requirements.
2 | RFP | 1.5/p.5 | Please consider a one week extension to the question period. | A one-week extension was granted changing the end of the Question and Answer period from February 14, 2020 to February 21, 2020.
1 | RFP | 1.4, page 5 | Is there a preferred level of equipment reuse that the RMA would like to see? | No, there is not a preferred level.
2 | RFP | 1.4, page 5 | Is there specific equipment that the RMA does NOT want to be reused? | No, there is no specific equipment that NET RMA does not want used.
3 | RFP | 3.7, page 23 | How many workstations does the TSI need to supply as part of this procurement? | None
4 | RFP | 3.8.3, page 29 | Is the use of monochrome front imagers combined with color rear imagers acceptable? | There are no color cameras on Toll 49.
5 | RFP | 3.9.2, page 36 | Is a transaction adjustment capability required as part of the TFH functionality? If so, which data is to be adjusted at this level? | There is no transaction adjustment desire or required. Transactions, in their entirety are pass to the CTRMA Host.
6 | RFP | 3.9.2, page 36 | If an adjustment capability is required at the Toll Host, how is this synchronized with adjustments performed at the BOS? | There is no transaction adjustment desire or required. Transactions, in their entirety are pass to the CTRMA Host.
7 | RFP | 3.9.4, page 38 | Is there a NETRMA data center available to house the TFH? | No
8 | RFP | 3.9.4, page 38 | Where is the TFH currently located? | In a roadside cabinet at SH 64 main line. See Addendum #2
9 | RFP | 3.9.5.3, page 41 | Is it acceptable to have both the TFH and the DR site as cloud based? | Yes
10 | RFP | 3.9.5.2, page 40 | Does the RMA have a preferred DBMS? Is there any DBMS that the RMA would reject? | No. NET RMA would not reject A DBMS that meets are all requirements.
11 | Appendix C |  | How are alternate solutions to be proposed? (e.g. all color VES with an alternate of IR and Color VES) | Section 3.8.3.1 requires description of TSI solution. If an alternate solution is proposed please describe it here.
12 | Appendix C |  | For the response sections labeled (“No response required for this section”) is it acceptable to provide additional information if it clarifies our solution? | No. Please adhere to the instructions.
13 | Appendix D | Schedule A | Is NET RMA Tax Exempt? | Yes
14 | Appendix D | Schedule A | At the completion of which Milestone/Task will the 10% Retainage be returned? | At successful completion of System Acceptance Testing.
15 | RFP | 3.9.5.1/p.40 | Is the use of Server Virtualization accepted for the main site and DRS deployment? | Yes
16 | Appendix J | p1 | Do Video Audit System files need to be backed up also in the DRS? | No
17 | RFP | 3.2.1 | For the purpose of evaluating the existing equipment, would it be possible for NET RMA to share the maintenance records from the last 5 years? | No. NET RMA will not seek or provide five years of maintenance records. Please use the equipment workbook, which provides date placed into service and your knowledge of equipment life cycles.
18 | RFP | 3.2.3/19 | Cabinets to be reused - For the refurbishment of cabinets it could be relevant to use spare cabinets in order to advance works in factory whenever possible. Will NETRMA make such spare cabinets available? | Yes
19 | RFP | 3.2.3/19 | Related with overview images - the vehicles axles must be visible in the overview images? | No, the axles do not need to be visible in the overview image. Automated vehicle classification will rely on a separate sub-set of lane equipment.
20 | RFP | 3.9.3.2/ 38 | Considering that there are no specific requirements for the integration with the Central US IOP Hub, it becomes impossible to provide the required pricing within customary business risk ranges. Would it be acceptable for the proposer to propose an alternative compromise? | No. The RFP states in Section 3.9.3 requires pricing. The RFP provides the NIOP ICD for consideration in pricing.
21 | RFP | 3.14.1/ 61 | In the current 'Priority 1' definition NET RMA is including "fault that will result in the loss of revenue". Shall we assume that any loss of revenue would position the incident in 'Priority 1', irrespective of the value? Example: Loss of revenue in a shoulder lane typically is not considered priority. | Yes. Any potential loss of revenue is a Priority 1 event.
22 | RFP | 3.14.4/ 63 | In point 5) NET RMA is including "Desktop Support" - Could you please clarify what support is expected and the number of desktops to be supported? | Desktop support is intended to assist NET RMA staff with questions about the system or system access during normal business hours, Central Standard Time.
23 | Appendix G NETRMA Equipment for RFP | page 5 to 16 | TNL-50 Traffic Night Flash part # 31015649 for all gantries - This part number is for IR Flash but during the last visit we have saw some blue flashes, not IR. Can you please clarify the correct part numbers for each installation? | Updated part # for the blue flash strobes; 'TNL-50 Blue LED flash for lane illumination part # 31015651. PCM and both SH-64 ramps are still using the old JAI 400 Cameras with the Purple strobes
24 | Appendix E | SLA ID 8/ 2 | Could you please clarify your understanding of "incorrect code-off results"? | Both SLAs 7 and 8 do not apply. Please disregard in your response. Image review is not in the scope of work for this contract.
25 | Appendix B. Contract | Appendix B. Contract | This document states that the contract will be provided via an RFP Addendum. Since no contract has been received so far, will proposers be granted additional Q&A period? | No
26 | Appendix E | Appendix E | What are the last three results and dates occurred for the current system SLAs? | The current TSI has not measured the current using the proposed SLAs. The system by and large meets the current required SLAs
27 |  |  | a. Detecting vehicles at speeds in accordance with the SLA requirements | See above
28 |  |  | b. Separating vehicles at speeds in accordance with the SLA requirements | See above
29 |  |  | c. Classifying vehicles at speeds in accordance with the SLA requirements | See above
30 | Appendix E | Appendix E | What are the reports and SLAs required for the Digital Video Audit System (DVAS)? Please provide a copy of the latest report. | There are no SLAs for DVAS.
31 | RFP | 3.14.1 General Requirements | All network equipment and cables, including the roadside Fiber Optic Network. AT&T will maintain the network; however, the TSI shall be responsible for monitoring and notifying AT&T if outages or issues occur.
32 |  |  | Could NET RMA provide the last 12 months of trouble tickets submitted to AT&T? | No. AT&T is completing installation of the new fiber network. There is no maintenance to date.
33 | Appendix L | Appendix L | Is there any system outage alert messaging exchanged between CTRMA, CUSIOP, and other integrated partners? | No
34 | RFP | 3.13.7 | Is NET RMA going to perform SAT (System Acceptance Testing) along with TSI? Or NET RMA is going to monitor only Test Results of SAT performed by TSI? | NET RMA will monitor all testing, including SAT.
35 | RFP | 3.8.3 | This procurement doesn't call out specifications on the cameras being used aside from requiring color. There is potential for TSI's to offer low resolution solutions that doesn't provide coverage across the width of full lanes or straddle zones with multiple cameras nor is there a requirement for pixels per plate. Is there an omission regarding these areas? | Section 3.8.3 #4 requires captured images must include legible license plate information and vehicle image data. TSI needs to offer their best solution to meet the requirement.
36 | RFP | 1.8 | Can the bond requirement be an annual renewable bond in the amount of work to be performed each year of the 5 years contract? | NET RMA agrees to an annual bond, renewable each year in the amount of annual maintenance. The requirement for a performance bond “equal to 100% of the contract price,” for the entire implementation phase remains the requirement.
37 | RFP | 3.2/p18 and 3.2.6/p20 | RFP 3.2 states: NET RMA makes no assertion regarding the condition, functionality or performance of installed equipment. No installed equipment is currently warranted by NET RMA. It is incumbent on the TSI to determine the condition and fitness for use of any currently installed equipment which will be reused. RFP 3.2.6 states: This list of existing equipment acceptance shall be delivered to NET RMA no later than 90 days after NTP, in accordance with Appendix K – Project Deliverables Schedule, and will communicate all existing equipment defects affecting functionality or performance..... NET RMA will inspect each claimed defect within 10 business days and determine the appropriate action (e.g., repair, replace, retain as is) and the timing of the action. Any agreed upon repair or replacement work may be performed via a change order with the TSI. The way 3.2.6 is written NET RMA provides a 90 days warranty on installed equipment chosen to be reused by the TSI whereas 3.2 that no equipment is currently warranted by NET RMA. Please clarify what applies. | No equipment is warranted by NET RMA. The TSI is given the first 90 days after NTP to access the equipment and to provide a report of that assessment to NET RMA. NET RMA will respond to that report within 10 days.
38 | RFP | 3.2.5/p20 | RFP 3.2.5 states: The TSI may use the existing electrical system to minimize new work where possible, constrained by retaining existing electrical service to the legacy roadside equipment and devices during the transition to the proposed System. Any disruptions to the existing tolling system shall be coordinated with NET RMA. Is the disruption of legacy roadside equipment operation acceptable if coordinated with NET RMA? | Yes. TSI must schedule and obtain approval from NET RMA for disruptions to include the duration of disruptions.
39 | RFP | 3.7/p.23 | RFP 3.7 states: All TSI provided systems need to be compatible to run on NET RMA provided workstations and NET RMA designated representative-provided workstations. Please provide specs and OS version of NET RMA and NET RMA designated representative-provided workstations. | NET RMA uses Microsoft Windows 10 and Chrome.
40 | RFP | 3.7/p.23 | What are the existing system's acceptable down time during transition? | TSI must coordinate any down time with NET RMA and should run concurrently with maintenance or installation activities. All lane closures will occur at night between 9:00 p.m. and 5:00 a.m.
41 | RFP | 3.8.1.2/p26 | RFP 3.8.1.2 states: All messages between the Zone Controller and the VES (e.g., OCR data, triggers, transaction link data), AVI, AVD, and AVC subsystems, and the TFH shall use a documented, non-proprietary protocol that is made available to and approved by NET RMA during the Design Phase of the Project. Does this requirement exclude roadside equipment with vendor proprietary protocols for communication? | No, it doesn’t exclude a vendor’s proprietary protocols. The goal here is for NET RMA to have a productive conversation about integrating either different lane components (cameras, AVI readers, loops/lasers, etc.) or using a different host (TFH) to accept the zone controller messages.
42 | RFP | 3.9.5.1/p.40 | Is the use of Server Virtualization accepted for the main site and DRS deployment? | Yes
43 | Appendix J | P1 | Do Video Audit System Video files need to be backed up also in the DRS? | No